## Work Progress
SocialPulse - Work Progress & Development Journey
Simple record of the work completed, current progress and next steps
S.No. | Module / Feature | What I Did | Status | Main Challenge | How I Solved It | Next Step
1 | Content Studio UI (8-step Studio) | Extended Content Studio from 6 to 8 steps: Idea, Settings, Content, Media, Design, Branding & Accessibility, Preview, Publish with premium SaaS redesign per step. | Done | The page was looking too crowded and confusing. | Split Media into Media + Design + Branding, rebuilt Steps 1-4,7,8 with two-column premium UI (no route logic moved). | Keep refining only the UI where needed.
2 | AI Content | Kept AI-generated caption, hashtags and image prompt editable before publishing. | Done | AI content should not go directly for publishing without review. | Added user review/edit before Preview and Publish. | Use only final edited text while publishing.
3 | AI Image Generation | AI image generation with gated premium loader (Thinking + 0-97 hold, 99->100 reveal, canvas particle field) and lost-job 404 handling. | Done | Needed generated image to fit the selected social-media ratio. | Added src/app/ai-image-loader.tsx (canvas, 300-1500 dots, gated progress) + pollImageJob 404 handling; no provider change. | Continue testing all ratios.
4 | Image Upload + Caption | Enabled uploaded image to be used for generating caption/text. | Done | Uploaded image and generated image had different flows. | Reused the existing image-to-text/vision flow. | Connect this smoothly with Canva editing.
5 | Media Upload | Added image/video upload, preview and media reordering. | Done | Multiple media items were difficult to manage on one screen. | Used one common Media section with reorder/delete/preview. | Keep all future integrations using the same Media section.
6 | Logo Branding | Added logo branding on generated/uploaded media. | Done | Logo placement had to work on different image sizes. | Used fixed supported logo positions and preview before publish. | Refine size/position controls if required.
7 | Carousel Editor | Completed the carousel workflow with 2–9 image slides, manual selection, AI generation of multiple slides, reorder/remove controls, swipe preview and publish readiness. | Done | Needed one carousel flow that worked across multiple platforms without building a full Canva-like editor. | Reused the common Media flow and preserved slide order through preview, scheduling and publishing. | Continue polishing carousel UI and Canva handoff.
8 | LinkedIn Integration | Connected LinkedIn using official OAuth and API. | Done | LinkedIn account got temporarily restricted during testing. | Completed account verification, stopped repeated testing and kept only official OAuth/API usage. | Continue only controlled publishing tests.
9 | LinkedIn Permissions | Configured OpenID Connect and w_member_social / Share on LinkedIn. | Done | Login permission alone was not enough for publishing. | Added the correct LinkedIn product and publishing permission. | Keep the permissions minimal and valid.
10 | LinkedIn Publish Safety | Removed the old 30-second automatic LinkedIn publishing flow. | Done | Repeated/automatic activity could increase restriction risk. | Kept publishing as an explicit user action. | Do not reintroduce unattended LinkedIn publishing.
11 | Duplicate Publish Protection | Implemented one click = one publish request, disabled Publish while active, no hidden retry and a 10-second cooldown. | Done | Double-clicks or retries could create duplicate posts. | Added publish guards, cooldown and unique publish-attempt handling. | Keep regression-testing publish safety after future platform changes.
12 | LinkedIn Media Error | Changed the requirement so failed media upload should not silently post text only. | In Progress | Image/video failure could create an unexpected text-only post. | Stop publish and show a clear media error. | Verify image and video failure cases.
13 | LinkedIn Disconnect | Implemented real LinkedIn disconnect behavior that removes the saved token/connection state. | Done | UI-only disconnect could leave the account effectively connected. | Disconnect now clears the stored connection state instead of only changing the interface. | Retest disconnect/reconnect whenever LinkedIn OAuth is changed.
14 | Canva Developer Setup | Created Canva Connect API integration for SocialPulse. | Done | Canva required MFA before creating the integration. | Set Canva password, enabled Authenticator MFA and then created the integration. | Keep testing in Draft mode.
15 | Canva Permissions | Selected Canva asset/design/profile permissions required for the project. | Done | Needed enough access without selecting unnecessary permissions. | Selected only asset read/write, design content read/write, design meta read and profile read. | Avoid adding extra scopes unless required.
16 | Edit in Canva | Current generated SocialPulse image can be opened in Canva for editing. | Done | Wanted Canva editing without changing the existing AI image generator. | Added Canva as an editing option for the generated image. | Verify return/import after edit.
17 | Upload → Text → Canva | Planned uploaded image → generate text → edit image in Canva. | In Progress | Needed image understanding and Canva editing in one flow. | Reuse current image-to-text feature and then send the same uploaded image to Canva. | Complete the full user flow.
18 | Create in Canva | Planned a Create in Canva option for starting a new design directly in Canva. | In Progress | Earlier Canva flow only edited a SocialPulse-generated image. | Added the requirement for a blank/new Canva design flow. | Implement and test return to SocialPulse.
19 | Import from Canva | Canva-returned media is now handled through the same common mediaItems workflow as uploaded and AI-generated media. | Done | Canva results needed to return without creating a separate media subsystem. | Reused the unified Media section so Canva-imported assets can continue to preview, carousel and publishing flows. | Improve the Canva return/sync confirmation UX.
20 | Meta App - Facebook/Instagram | Built the dedicated Meta Social app flow for Facebook/Instagram, including Facebook Login for Business configuration and status handling. | Done | Meta permissions and business assets required a different OAuth model from the initial scope-based approach. | Moved Facebook login to the working config_id flow and kept Instagram dependent on the linked Facebook Page. | Reconnect Facebook when needed and link a publishable Instagram Professional account.
21 | Meta OAuth Redirect | Configured and verified the public SocialPulse callback URLs behind the Cloudflare tunnel. | Done | Callbacks initially inherited the local 0.0.0.0 origin and Meta rejected/redirected incorrectly. | Derived callbacks from the configured public app URL and exact OAuth redirect URIs. | Keep production callback URLs synchronized with Meta settings.
22 | Facebook Page Publishing | Implemented and successfully tested Facebook Page publishing through the official Meta API. | Done | Publishing had to use the correct managed Page/token rather than a personal Facebook profile. | Resolved Page access through the Facebook Login for Business flow and reused the shared media/publish pipeline. | Reconnect Facebook through normal OAuth whenever the account is disconnected.
23 | Instagram Publishing | Completed Instagram Business publishing integration in SocialPulse and verified the platform connection/publish flow. | Done | Instagram Graph publishing requires a Professional account, correct permissions and reachable media URLs. | Completed the Graph API publishing path and aligned it with the shared SocialPulse media/publish workflow. | Keep regression-testing captions, media URLs and carousel behavior.
24 | Meta WhatsApp Cloud API | Created and verified the separate official Meta WhatsApp app, production WABA/phone setup and webhook path. Kept it isolated from Whapi. | Done | Official Meta Cloud API does not provide the same direct access to arbitrary existing WhatsApp groups/Communities required by SocialPulse. | Retained the official Meta integration for supported business messaging while using Whapi for existing-group publishing. | Keep Meta and Whapi providers separate and use each only for supported use cases.
25 | WhatsApp Existing-Group Publishing | Implemented direct publishing from SocialPulse to existing WhatsApp groups through Whapi Cloud. | Done | The requirement was to select an already-existing group and publish directly without operating a separate WhatsApp dashboard. | Added a Whapi backend adapter, real group discovery, group validation and direct SocialPulse publish flow. | Add scheduling/delivery-status polish after immediate publishing is stable.
26 | Multi-Platform Publishing | Unified publishing now covers LinkedIn, Facebook, Instagram and WhatsApp (Whapi), with Canva as the design/editing integration. | Done | Each platform has different OAuth, media, permission and publishing rules. | Kept one shared content/media workflow with separate server-side platform adapters and publish safety controls. | Run periodic end-to-end regression tests across all connected platforms.
27 | LinkedIn Company Page Publishing | Created a separate clean LinkedIn Developer App, 'SocialPulse Page Publishing', linked to the existing verified Dotstark Technologies Page to pursue organization-level posting. | In Progress | Community Management API Development Tier shows Request access as disabled even on the new clean app. | Kept the existing working personal LinkedIn app untouched and isolated Company Page publishing into a separate approval path. | Raise the LinkedIn Developer/partner access request and obtain Community Management API approval.
28 | LinkedIn Organization Publishing Architecture | Defined the future SocialPulse flow for publishing as either a personal profile or an authorized LinkedIn Company Page. | Planned | Organization publishing needs LinkedIn approval, organization scopes, Page authorization checks and organization-aware media ownership. | Prepared a backward-compatible design using targetType person/organization and server-side authorization validation. | Implement only after Community Management access is approved; then reconnect OAuth once.
29 | Canva UX Redesign | Redesigned the Canva experience conceptually so it appears as a first-class 'Design with Canva' feature rather than only a connection block. | Planned | The current Canva area looks more like an authentication/settings row than a creative workflow. | Defined Create in Canva, Edit Selected in Canva and Import from Canva actions, contextual media buttons and a clearer carousel/branding layout. | Implement the approved Canva UI without changing the working backend integration.
30 | SocialPulse Live Tunnel | Moved the active project to the current SocialPulse repo and verified the public Cloudflare tunnel at socialpulse.dotstark.tech for OAuth/webhook callbacks. | Done | External OAuth providers and WhatsApp webhooks need a stable public callback instead of localhost. | Configured the public app URL and platform redirect URIs to use the live tunnel. | Keep the tunnel/domain configuration stable while integration testing continues.
31 | Whapi Channel Connection | Connected a WhatsApp account to Whapi Cloud using a QR-linked channel and configured the server-side API base/token in SocialPulse. | Done | Credentials must never be exposed to the browser or logs. | Stored the Whapi token only in server-side environment variables and used a dedicated client helper. | Rotate tokens if exposed and keep channel health monitoring.
32 | Whapi Existing Group Discovery | Added /api/whapi/groups to fetch and normalize real existing WhatsApp groups, Communities and announcement-group metadata. | Done | Personal chats must not appear in the group picker, and Community parent IDs can differ from announcement destinations. | Filtered to group-style destinations, stripped unnecessary participant data and preserved destination type metadata. | Paginate beyond the first page when needed and keep destination names refreshed.
33 | Whapi Group Publishing | Added /api/whapi/publish and verified a real existing-group text message from SocialPulse end to end. | Done | A UI-only integration was not sufficient; real WhatsApp delivery had to be proven. | Validated the selected @g.us group against Whapi before sending and confirmed visible delivery in the target group. | Keep one-click publishing explicit; add scheduling separately.
34 | Whapi Media + Caption Publishing | Verified image + caption and video publishing to an existing WhatsApp group through Whapi. | Done | Media publishing must preserve the SocialPulse final text as the image/video caption instead of silently dropping it. | Mapped SocialPulse text to the media caption and used the Whapi media endpoints. Unsupported fake carousel behavior is avoided. | Improve multi-media behavior only after validating Whapi's supported message model.
35 | Whapi Webhook & Safety | Created a dedicated /api/whapi/webhook and added duplicate-request protection, publish cooldown, group validation and sanitized logging. | Done | Whapi webhook payloads differ from Meta WhatsApp, and retries/double clicks can create duplicate posts. | Kept Whapi and Meta webhooks separate, added attempt-ID duplicate protection and retained one-click = one publish. | Use webhook status events later for Sent/Delivered/Read UI where available.
36 | Whapi Trial / Plan Limits | Observed HTTP 402 trial-version limits when publishing to additional groups even though the integration itself was working. | In Progress | Whapi trial/channel entitlement can restrict active conversations/groups and block otherwise valid publishing requests. | Handled the provider error clearly in SocialPulse and started testing with a fresh trial/channel while keeping code unchanged. | Choose the appropriate Whapi plan/channel entitlement for production and retest multiple destination groups.
37 | Whapi Community Announcement Support | Normalized Community and announcement-group metadata so SocialPulse can target a dedicated announcement-group ID when Whapi exposes it. | In Progress | A Community parent ID is not necessarily the directly messageable destination. | Preserved isParent/isCommunityAnnounce/linkedParent metadata and avoided messaging parent Community IDs directly. | Complete one real Community announcement publish test and then expose the destination cleanly in the UI.
38 | Studio 8-Step Redesign | Redesigned Steps 1-4,7,8 to premium UI and created new Steps 5 (Design Studio) and 6 (Branding & Accessibility) as dedicated pages | Done | Media page was overloaded with Canva/Carousel/Branding/ALT in one place | Moved Canva/Carousel to Step 5, Branding/ALT/Logo/Colors/Fonts to Step 6 with strict page separation | Keep 8-step flow as canonical; future edits page-scoped
39 | Design Studio (Step 5) | Moved Design with Canva, Single/Carousel selection and slide arrangement into dedicated Step 5 | Done | Design controls were duplicated across Media and Branding | Removed branding/ALT from Media, isolated Canva + carousel logic to Step 5 | Polish Canva handoff, keep no duplication
40 | Branding & Accessibility (Step 6) | Created Step 6 for Brand Logo/Colors/Fonts + Brand Readiness + branded Design Preview + ALT Text | Done | Branding logic was tangled with Media/Design previews | New Page 6 with clean preview (live logo overlay math + platform dropdown) and ALT controls only there | Keep branding preview in sync with Step 5 media
41 | AI Gated Image Loader | Implemented gated progress: 0->97 over 14s, hold 99 until backend ready, 99->100 sprint + brighten + 450ms fade + 0.97->1.00 scale | Done | Plain spinner hid actual vs perceived progress; fast backend revealed image too early | src/app/ai-image-loader.tsx (canvas, requestAnimationFrame, hidden-tab pause, reduced-motion) + genGate/genRunId/genFinishing gate in StudioWizard | Tune 14s floor if median generation shifts
42 | WhatsApp Admin Error Handling | Surfaced Whapi 403 group-announce-not-admin as clear admin message instead of generic failure | Done | Publishing image to announcement group where number is member (not admin) returned 403 forbidden, shown as generic 'could not publish' | Mapped 403 details in whapi/client.ts + preserve 403 in whapi/publish + specific toast in whatsapp/publish + page.tsx | Instruct users to choose regular All groups or make number admin
43 | WhatsApp Communities Picker Fix | Fixed Communities+All groups merge: resolve via /communities/{id}/subgroups → announceGroupInfo.id, tolerate slow communities (8-22s) without hiding groups | Done | Communities grew to 13/169 groups; merge echoed parents as announcement_group and blocked groups on failure; groups hid when communities slow | Prefer /communities + subgroups, tolerant loadWhapiGroups (commOk branch), dedup by id trusting /groups typing | Keep picker as Community (13) + All groups (~156); add subgroup cache if needed
44 | Double Hashtag Publishing Fix | Fixed WhatsApp double hashtags (14 instead of 7) where content already contained tags | Done | content = caption + hashtags, then publishToWhapi appended same hashtags again | Added stripTrailingHashtags() and rebuilt all publish paths from stripped caption + single block | Keep single-append invariant; regression test publishing
45 | Logo Replace-not-Stack Fix | Fixed Change logo stacking and double-logo preview (burned + overlay) | Done | Empty-gallery apply used random id under gen, later Changes burned on stale bytes and stacked; overlays checked gen flag missing, showing both | Stable GEN_ID=gen-logo, replace-in-place, flag both GEN_ID+gen, clearLogo restores originals, geometryTouchedRef guard | Verify 10-step logo test (Apply A->B/C-> geometry->Remove) stays single
46 | Image Job Lost Handling | Fixed Lost track of the image job — please try again overlay after dev restart | Done | In-memory jobs Map cleared on restart; poll threw unhandled error to Turbopack overlay | pollImageJob now returns error object on 404/transient instead of throw; no overlay | No action — jobs remain in-memory; move to persistent store for prod

## Challenges & Solutions
Major Challenges Faced During SocialPulse Development
S.No. | Area | Challenge | What Happened / Impact | How I Overcame It | Result / Learning
1 | UI | Content Studio was too crowded | Too many controls were visible together and the screen looked heavy. | Changed the screen into a step-by-step wizard. | Cleaner and easier user flow.
2 | LinkedIn | Account got temporarily restricted | Testing image publishing triggered LinkedIn security/restriction flow. | Stopped repeated attempts, completed verification and used only official OAuth/API. | Testing became more controlled and safer.
3 | LinkedIn | Automatic publishing risk | Old 30-second scheduler could publish without direct user action. | Removed the automatic LinkedIn publishing flow. | Publishing is now user-controlled.
4 | LinkedIn | Duplicate post risk | Multiple clicks/retries could send the same publish request more than once. | Added requirement for one click = one request, button disable and no hidden retry. | Duplicate activity risk reduced.
5 | LinkedIn | Media failure could become text-only post | If image upload failed, the post could still go as text. | Changed behavior so media failure stops the post and shows an error. | More predictable publishing behavior.
6 | Security | Client secret exposure risk | Secrets can appear in screenshots or frontend code. | Keep secrets/tokens server-side and rotate any exposed secret. | Better credential safety.
7 | Canva | MFA was required | Canva did not allow Connect API integration creation without MFA. | Created a password and enabled Authenticator MFA. | Canva integration creation succeeded.
8 | Canva | Wrong integration approach initially | Canva Button was suggested first but was not the right path for this project. | Moved to official Canva Connect APIs. | Correct integration architecture selected.
9 | Canva | Need more than just Edit in Canva | Current flow only edits SocialPulse-generated images. | Planned Create in Canva, Import from Canva and Upload → Text → Canva workflows. | Canva will become a full optional design source/editor.
10 | Meta | Facebook Login and WhatsApp use cases conflicted | Meta did not allow the selected use cases together in one app. | Created separate Social and WhatsApp Meta apps. | Cleaner permissions and setup.
11 | Meta | Redirect URI invalid | Facebook Login validator rejected the callback URL. | Added the exact SocialPulse callback under Valid OAuth Redirect URIs. | OAuth configuration path became clear.
12 | Architecture | Too many integrations can create duplicate media flows | LinkedIn, Canva and Meta could each create separate media handling. | Kept one common Media section and reused existing media state. | Simpler maintenance and consistent UI.
13 | LinkedIn | Company Page API access is gated | A brand-new clean LinkedIn app linked to Dotstark Technologies still shows Community Management API Request access as disabled. | Kept personal posting live in the existing app and created a separate clean Page Publishing app for the approval process. | The blocker is now LinkedIn product approval, not a SocialPulse coding bug.
14 | WhatsApp | Official Meta Groups API eligibility / existing-group mismatch | The official Meta WhatsApp route could not satisfy the requirement to publish directly to arbitrary existing WhatsApp groups, and API-created groups were subject to eligibility/OBA constraints. | Kept the official Meta Cloud API integration separate and added Whapi as the dedicated existing-group provider. | SocialPulse now supports the required existing-group workflow without removing the official Meta integration.
15 | Instagram | Graph API media/account requirements | Instagram publishing required a Professional account, correct Graph permissions and media that the API could access. | Completed the Instagram publishing path and aligned media/account handling with the shared SocialPulse workflow. | Instagram integration is working; continue regression-testing media and carousel edge cases.
16 | WhatsApp / Whapi | Needed direct publishing from SocialPulse instead of manual Whapi dashboard usage. | The client would otherwise have to leave SocialPulse, find the destination and send manually. | Implemented Whapi only as a server-side API layer behind SocialPulse, including group discovery and direct publish. | Client now selects an existing group and publishes from SocialPulse; Whapi remains behind the scenes.
17 | WhatsApp / Whapi | Whapi UI was reported as complete but was not visible in the live Step 6 screen. | Backend tests passed, but the actual rendered wizard did not initially expose the WhatsApp group selector/publish card. | Debugged the real rendered component/prop path and required live visual verification instead of code-presence claims. | Frontend completion must be verified in the running application, not only in source code.
18 | WhatsApp / Whapi | Trial plan blocked publishing to additional groups with HTTP 402. | A valid publish request reached Whapi but the provider rejected the destination because of trial/channel entitlement limits. | Kept the SocialPulse integration unchanged, surfaced the provider error clearly and tested a fresh Whapi trial/channel. | Provider plan limits are separate from application correctness; production needs suitable Whapi entitlement.
19 | WhatsApp / Whapi | Image/video publishing must keep the generated post text. | A media-only request could make it appear that Whapi does not support image + text. | Mapped the final SocialPulse text into the Whapi image/video caption field and verified image + caption delivery. | Text-only uses text messaging; image/video + text uses the media caption.
20 | Architecture | Official Meta WhatsApp and Whapi serve different requirements. | Meta Cloud API is appropriate for official business messaging but does not satisfy the same arbitrary existing-group workflow. | Kept /api/whatsapp/* for Meta and /api/whapi/* for existing-group publishing, with separate webhooks and credentials. | Provider separation reduces regressions and keeps future Meta/Whapi features maintainable.
21 | WhatsApp / Whapi | Announcement group 403 (not admin) | Publishing image to Testerrrrrrrrrrrr announce returned 403 group-announce-not-admin; shown as generic failure | Added specific 403 mapping in whapi/client + preserve in publish routes + clear toast copy | Choose regular group or make number admin; verified Garvvvvv sent:true vs announce 403
22 | Content | Double hashtags in WhatsApp posts | WhatsApp image showed 14 tags (each duplicated) as in user screenshot | content already had hashtags then publish appended again; added stripTrailingHashtags() and deduped all publish paths | Single hashtag block now; tested with Sony speaker example -> 7 tags
23 | Media | Logo stacking / double logo preview | Change logo created second branded image and preview showed stacked burned+overlay logos | Stable GEN_ID, replace-in-place, flag gen+GEN_ID, restoreBurnedMedia on Remove/geometry | 10-step logo test passes; future burns always from clean original
24 | Media | Image job lost after dev restart | "Lost track of the image job" Turbopack overlay after next dev restart cleared Map | Made pollImageJob tolerant: 404 returns error object, not throw; transient retries | No overlay; user clicks Generate again for fresh job
25 | UI | 6→8 step workflow required strict separation | Media/Design/Branding controls were duplicated across pages | Moved to 8-step flow with page-scoped controls (Media only upload/generate, Design only Canva/carousel, Branding only logo/colors/fonts/ALT) | Keep page separation invariant

## Quick Summary
SocialPulse - Current Progress Summary
Status | Count
Done
In Progress
Planned
Total Items
Immediate Focus | 1 | 2 | 3
Next Work | Whapi production plan + multi-group reliability | LinkedIn Company Page approval | Cross-platform regression + scheduler/draft hardening
WhatsApp / Whapi Client Flow
Client | Creates/selects content in SocialPulse and chooses an existing WhatsApp destination
SocialPulse Backend | Validates the selected group and securely sends the request through the Whapi adapter
Whapi Cloud | Acts as the linked-device WhatsApp API layer for existing groups/Community announcement groups
WhatsApp | Publishes text, image + caption or video to the selected existing group
Current status | Existing-group publishing is live-tested; trial/plan limits may restrict additional groups

## Models & AI Stack
SocialPulse - Models & AI / Integration Stack
Record of the AI models/services and external APIs currently used or planned in SocialPulse.
S.No. | Feature / Purpose | Model / Service | Provider | Type | Status / Notes
1 | Mercury 2.5 (primary) → Nemotron 3.5 Lightning (fallback) | mercury-2.5 | Inception Labs (primary) / NVIDIA (fallback) | LLM / Text Generation | Implemented via POST /api/generate-content. Primary: Inception api.inceptionlabs.ai/v1 mercury-2.5 (reasoning_effort low). Fallback: NVIDIA integrate.api.nvidia.com nvidia/nemotron-3.5-lightning-30b-a3b. 120s timeout. Verified 2-5s primary, fallback on unparseable/timeout.
2 | Image-to-Text / Vision + Caption | meta/llama-3.2-11b-vision-instruct (only) | NVIDIA | Vision / Multimodal | Implemented for uploaded/reference-image understanding. Two-step: direct multimodal race (60s) → analyze separately (45s) → Mercury→Nemotron text. Sharp normalize to 1024px JPEG. Single vision model (minimax-m3 was end-of-life 2026-09-09, 410 Gone).
3 | AI Image Generation (gated) | gpt-image-2 | Pollinations.AI (gen.pollinations.ai) | Image Generation API | Implemented as background job + polling (POST -> jobId 202 + poll 2.5s). No server timeout. Gated loader holds result until progress 99->100 reveal (Thinking + canvas particle field).
4 | WhatsApp Existing-Group Publishing | Whapi Cloud | Whapi Cloud | REST API / WhatsApp linked-device integration | Implemented and live-tested for real existing groups. Supports group discovery plus text, image + caption and video publishing. Uses a separate /api/whapi/* backend and server-only token.
5 | Official WhatsApp Business Integration | Meta WhatsApp Cloud API | Meta | Official Business Messaging API | Kept separately under /api/whatsapp/*. Useful for official WABA/business messaging; not used as the arbitrary existing-group publishing path.
6 | Facebook / Instagram Publishing | Meta Graph API | Meta | Social Platform API | Implemented for Facebook Page and Instagram Professional publishing within the shared SocialPulse workflow.
7 | LinkedIn Publishing | LinkedIn API | LinkedIn | Social Platform API | Personal publishing is working. Company Page publishing remains dependent on LinkedIn Community Management/organization access approval.
8 | Canva Design Integration | Canva Connect API | Canva | Design API | Implemented for Canva edit/import workflows and integrated into the common media pipeline.
Important
• Exact AI model IDs above are from current SocialPulse backend (.env.local + src/app/api/generate-content/route.ts): Mercury 2.5 primary → Nemotron fallback; Llama 3.2 11b vision only; gpt-image-2 gated.
• Whapi Cloud is not a Meta-official Cloud API; it is a separate linked-device/session integration used specifically for existing WhatsApp groups/Communities.
• Meta WhatsApp Cloud API and Whapi remain isolated in separate backend routes and webhook paths.
• Whapi trial/plan limits can block additional destinations with HTTP 402 even when SocialPulse code is functioning correctly.
• Secrets/tokens for Whapi, Meta, LinkedIn and Canva must remain server-side and must not be exposed in client code or screenshots.